## Sheet1
Last modified: March 18, 2022
LAYOUT PROJECT: Farmstead
| Team size: 2 | Name
1. Le Nguyen Anh Tu (Leader)
2. Tran Duc Thanh
| Tasks Name | Start Build | Finish Build | % Build | Names | Start Testing | Finish Testing | % Testing | Names | Notes
| Features Section | 2022-03-04 | 2022-03-07 | 100% | Tu | 2022-03-07 | 2022-03-16 | 100% | Tu | − Check layout − Check responsive design − Modify Javascript effects − Modify some incorrect responsive design − Modify some incorrect effects
| Testimonials Section | 2022-03-09 | 2022-03-09 | 100% | Tu | 2022-03-09 | 2022-03-15 | 100% | Tu | − Check layout − Check responsive design − Modify some incorrect responsive design
| Footer | 2022-03-09 | 2022-03-10 | 100% | Tu | 2022-03-10 | 2022-03-15 | 100% | Tu | − Check layout − Check responsive design − Modify some incorrect responsive design
| Works Section | 2022-03-10 | 2022-03-11 | 100% | Thanh | 2022-03-11 | 2022-03-15 | 100% | Tu | − Check layout − Check responsive design − Modify some incorrect responsive design
| Services Section | 2022-03-14 | 2022-03-15 | 100% | Thanh | 2022-03-15 | 2022-03-15 | 100% | Tu | − Check layout − Check responsive design − Modify some incorrect responsive design
| Products Section | 2022-03-15 | 2022-03-15 | 100% | Tu | 2022-03-15 | 2022-03-15 | 100% | Tu | − Check layout − Check responsive design − Modify some incorrect responsive design − Modify some incorrect effects
| Header | 2022-03-14 | 2022-03-14 | 100% | Thanh | 2022-03-18 | 2022-03-18 | 100% | Tu | − Check layout − Check responsive design − Modify some incorrect responsive design − Add Javascript to effects on header
| Carousel Section | 2022-03-17 | 2022-03-17 | 100% | Tu | 2022-03-18 | 2022-03-18 | 100% | Tu | − Check layout − Check responsive design − Modify some incorrect responsive design